## Slide 1: Northern Integrated Supply Project (NISP) Water Literate Leaders– November 2023
Carl Brouwer
NISP Program Manager

## Slide 2
Final Environmental Impact Statement Purpose & Need
To provide the Project Participants with approximately 40,000 acre-feet of new reliable municipal water supply annually through a regional project coordinated by the District, which will meet a portion of the Participants’ current and reasonably projected future additional water supply needs.
Why NISP?
Notes: Carl

## Slide 3: NISP at a Glance
40,000 AF per Year
2 New Reservoirs
80 Miles of Pipelines
7 Miles of Highway 287 Relocation
Paid for by 15 Participants
Approx. $2B Total
$110M Cost to Date

## Slide 4: Glade Reservoir - Details
Dam
  170,000 AF of storage
  280-foot-tall Earth/Rock fill
  Material all on-site
  Approximately 18M cy of fill
40,000 Hp Pump Station
Munroe Canal Relocation
1,500 AF Forebay
Poudre Valley Canal Enlargement

## Slide 5: Glade Reservoir Advancement
Advancing towards 90% Design
Coordination with State & Technical Advisory Panel
www.NISPwater.org
Notes: Steph

## Slide 6: Highway 287 Relocation
Critical Path for Glade Reservoir
Advancing Towards 90% Design
Hired SEMA as CM/GC
Complete Land Purchases

## Slide 7
Delivery Conveyance Refinement
12 Miles of Poudre River
Year-Round Deliveries
Approximately 1/3 NISP Yield
Eliminates Dry-up Points
Required New Colorado Law
Improves Environment

## Slide 8: Galeton Reservoir
45,600 Acre-ft
75 Feet Tall Dam
1,700 Acres
All Land Purchased
Expandable to 81,000 Acre-ft

## Slide 9: Ditch Substitution & Exchange
New Cache and Larimer & Weld to Poudre Valley Canal
Fraction of their total diversions
Compensate ag companies for benefit of shareholders

## Slide 10: Permitting
2004
2008
2016
2018
2020
2015
2017
2018
Participant Group Formed
Federal NEPA Process Begins
Draft EIS Released
Supplemental Draft EIS Released
Conveyance Refinement Added
State FWMEP Approved
Final EIS Released
State Reservoir Release Bill
State 401 Water Quality Certification
404 Permit
2022
2003

## Slide 11: Permitting Status
State Fish and Wildlife Mitigation and Enhancement Plan
State 401 Certification
Larimer County 1041
Federal 404 Permit

## Slide 12: Clean Water Act Section 404 Permit
Culmination of 19 years of Environmental Process Led by US Army Corps of Engineers
Cooperating Agencies – EPA, BLM, USFWS, Colorado DNR, CDPHE, CDOT, Larimer County
No-Action – 60,000 acres of Agricultural Dry-up
Numerous Alternatives Analyzed Considering Environmental Criteria
Biological Opinion from US Fish and Wildlife Complete
Fish and Wildlife Coordination Act with USFWS Complete
Programmatic Agreement for Cultural Resources with State Historic Preservation Office Complete

## Slide 13: Next Steps

## Slide 14: Allotment Contract and Finance Plan
Critical Path for Glade Reservoir
At 60% Design
Hiring a CM/GC
Land Purchases
Coordination
Allotment Contract for Units of NISP and Space in Glade
Funding Needed
2022 Dollars - $1,900 Million
  Glade, HW 287, Delivery Pipelines - $1,400 Million
  Galeton side - $500 Million
Spread over 5+ Years
Potential Sources
EPA WIFIA - Approved to Apply for 49% of Project Except HW 287
CWCB
Municipal Bonds
CWRPDA, Other, Grants?

## Slide 15: Finalize Glade/HW 287 Design
Complete Design by mid 2024
Select Contractor
Finalize Remaining Land Purchase

## Slide 16: Galeton – Water Secure
Obtain Substitution Agreements with Irrigation Companies
Complete Design
Continue Water-Secure Program Development
Construct
www.NISPwater.org

## Slide 17: Project Schedule
DESCRIPTION | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  | 
 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
RECORD OF DECISION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HIGHWAY 287 RELOCATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GLADE RESERVOIR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GLADE PUMP STATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NISP CONVEYANCE PIPELINES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GALETON PIPELINES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GALETON RESERVOIR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SCHEDULE KEY: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRELIMINARY DESIGN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FINAL DESIGN & PROCUREMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CONSTRUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Notes: Storing water in Glade by 2029